The Oil and Gas Static Equipment Maintenance procedures & Special Torquing and Blasting Devices

By Amr Abbass

Masters of Engineering University of Idaho

Abstract

The Maintenace of static equipment represent a challenge in all of the refinery ,petrochemical and oil gathering facilities accordingly this paper  was initiated to detail the maintenance procedures for the different static equipment and identifies the works steps for heat exchangers , ejectors , tanks ,heaters ,boilers and flares

Method Statement

- The Refinery Static Equipment

- Flares

|  | Job Step |  |  |
| --- | --- | --- | --- |
| Erect Scaffold for Blinding |  |  |
| Install battery limit blinds |  |  |
| Install flare blinds |  |  |
| Disconnect Tip |  |  |
| Remove Tip from Flare |  |  |
| Clean Tip and Top Flange |  |  |
| Inspect Tip Flare and Flare |  |  |
| Reinstall Tip |  |  |
| Fix Tip and Tight |  |  |
| Remove Blinds |  |  |
| Remove Scaffold & Area Clean |  |  |

- Heat Exchangers

Job Step

Erect Scaffolding

Remove Insulation as required

Isolate Connect Drain

Install Blinds

Disconnect Piping

Remove Channel bonnet (both inlet and outlet side)

Remove internal tube bundle expansion joint and install lock bolt

Remove tube bundle

Transport Tube bundle and Exchanger Parts to Shop / yard

Clean shell and all components

Offer inspection / Repair(if any)

Hydroblast Tube Bundle

Offer inspection / Repair(if any)

Inspect all Gasket Surfaces

Transport Bundle / Heads to Site

Install Tube bundle and test ring

Hydrotest Shell Side, Repeat Test as Required

Offer inspection / Repair(if any)

Remove test ring and fix inlet side bonnet

Install outlet side expansion joint(tighten expansion joint bolts)

Hydrotest Tube Side, Repeat Test as Required

Offer inspection / Repair(if any)

Install outlet side bonnet and tighten all flanges

Hydro test shell side(final)

Remove Blinds

Refit Pipes

Repair and Refit Insulation

Remove Scaffolding

Clean Area

Tank

Job Step

Erect Scaffolding

Isolate and Drain

Install Blinds

Open Manway

Remove LG & LT's as required

Install Lights Internally as required

Clean Vessel Internally

Inspect Internals

Repair as per Inspection

Clean and flush all connected nozzles

Remove Internal Lighting

Install LG & LT's

Close Manway

Remove blinds

Remove External Scaffolding

Clean Area

Filters

Job Step

Erect Scaffolding

Isolate Filter Elements " Install Blinds "

Remove Filter Heads

Remove and Clean Filter Elements

Clean Filter Shell Internally

Clean filter element / offer inspection

Install Filter Elements

Reinstall Filter Heads

Remove Blinds

Remove Scaffold

Clean Area Around Filter

- Boilers

Job Step

Erect External Scaffold

Install Blinds

Open Steam Drum Manways

Install Ventilation Equipment

Remove Valves and PSV's to Shop

Remove Sight Glass Float Chamber to Shop

Install Internal Lights

Remove Internals

Clean Steam Drum Internally for Inspection

Clean Steam Drum Parts for Inspection

Inspect and Repair as Required

Install Internals and Steam Drum Parts

Remove Internal Lights

Remove Ventilation Equipment

Close Steam Drum Manways

Install PSV's and Valves

Install Sight Glass and Float Chamber

Remove Blinds

Repair Insulation

Remove External Scaffold

Clean Area

- FIN FANs Job Step

Isolate and Connect Drain

Erect scaffold

Install Blinds

Remove Plugs : Selected 10 % of Total No

Remove Plugs : Balance 90 %

Clean Tubes & Fins by Hydroblasting

Offer Inspection-Corrossion / Repair as required

Remove Bank and transport to Shop-Yard for retubing Repair as required and transport to site and erect after Repair

Install Plugs : Selected 10 % of Total No

Install Plugs : Balance 90 %

Hydrotest Tubes, Repeat Test as Required

Offer Inspection / Repair as required

Remove Blinds & Clean Area

Remove scaffold & Clean Area

11

Coolers

| Job Step |
| --- |
| Erect Sacffolding |  |
| Remove insulation as required |  |
| Install Blinds |  |
| Remove channel head cover |  |
| Remove Channel head |  |
| Remove 'U' tube bundle |  |
| Transport bundle to workshop |  |
| Clean parts |  |
| Hydroblast tube bundle |  |
| Inspect all gasket surfaces |  |
| Install tube bundle in shell |  |
| Instlal channel head |  |
| Hydrotest shell side |  |
| Install channel head cover |  |
| Final tube side hydrotest |  |
| Remove blinds |  |
| Repair and refit insulation |  |
| Remove scaffolding & clean area |  |

Heaters

Job Step

Install Scaffold for Blinding / Isolation

Isolate / Drain

Install Blinds as required

Drop / Clean all heater burners and steam out connected lines

Offer Inspection / Repair as required

Remove Control Valves and transport to Shop

Open Mandoors(Both Radiation and convection sides)

Neutralize the tubes by soda ash

Erect internal scaffold and provide internal lighting

Clean Tubes, Weld Joints, U - Bends and Tube Sheet

Offer Inspection / Repair as required

Repair Refractory

Service Dampers (erect scaffold as required and remove after repair)

Hydrostatic Test Coils, Repeat Test as Required

Offer Inspection / Repair as required

Transport Control Valves to Site and Install

Remove internal scaffold

Clean internally get Operation clearance

Reinstall all burners Get Operation Clearance

Remove Internal Lights

Install Man Way Covers

Remove Blinds

Remove Scaffold Externally

House keep the area

- Pressure Vessel Job Step

Erect External Scaffolding as required

Isolate / Drain

Install Blinds

Open Hand Holes

Remove Sight Glass - Float Chamber & clean as required

Clean Vessel Internally

Inspect Internals / Repair as required

Install Sight Glass and Float Chamber

Close Hand Holes

Remove Blinds

Remove External Scaffolding

Clean Area

- Towers Job Step

Erect External Scaffolding & at Skirt Area

Isolate and Drain Vessel

Install Blinds & N2 Purge

Open Manway

Remove PSV

Remove & clean sight glass and float chamber(LG &LT)

Install Ventilation Equipment

Install Light Internally

Open Tray Hatchways

Remove complete tray segments

Erect Internal Scaffolding

Clean Trays, Down Commers

Remove Demisters and clean as required

Inspect Internals & Repair as Per Inspection

Reinstall Tray segments

Replace Damage Tray Valves

Reinstall Tray Hatchways

Connect Water Hoses & Flush all connected nozzles

Reinstall demisters

Remove internal scaffolding

Remove Internal Lighting

Remove Ventilation Equipment

Install PSV

Install sight glass and float chamber

Close Manway

Remove Blinds

Remove External Scaffolding

Clean Area including all platforms

- Bolting and Hydro blasting Equipment

- Hydraulic Torque wrench

From 130 ft/lbs to 60,000 ft/lbs the hydraulic torque wrench . lubrication and preventative maintenance, is required for safe operation Different varitey of machine are found in https://www.torcup.com/ and brief is as follows .

- Pneumatic Torque Wrench

The Pneumatic Torque wrench is identical to Hydraulic wrench but with less torque wrench but it is easier in the application and economical.

- Tensioning & Bolting

Those are  hydraulic, pneumatic and manual torque wrenches; hydraulic bolt tensioning; and all tools associated are utilized to achieve accurate bolting within identified torques.

- Hydroblasting Machines

High Pressure Diesel Water Jet Pump System  can produce High-Pressure, from 4,000 psi to 40,000 psi with different flow rates to meet all application of normal surface blasting till fully clogged heat exchanger tubes . different variety of Machine are found in https://www.nlbcorp.com/

Conclusion

The Oil Refinery contains a variety of Equipment from Tanks , Heat Exchangers , Pressure Vessels , Filters , Boilers and Heaters…etc.

Each Equipment has its own maintence procedures that vary between scaffolding erection , heavy lifts and special torquing and blasting procedures.The Study identify for each equipment its procedures and the paper could be a good reference for shutdown planners & cost estimators to identify the required works durations and resources and cost based on dimensiosn of the Equipment.

Reference

- Plant Equipment & Maintenance Engineering Handbook By Duncan Richardson · 2013

- Torcup web site https://www.torcup.com/

- NLB web site https://www.nlbcorp.com/

- Major Process Equipment Maintenance and Repair Heinz P. Bloch, ‎Fred K. Geitner · 1997

- Maintenance Engineering Handbook  By Keith Mobley · 2008

- Industrial Machinery Repair: Best Maintenance Practices Ricky Smith, ‎R. Keith Mobley

- Engineering Maintenance A Modern Approach By B.S. Dhillon · 2002